ACME Manufacturing – Salesforce Implementation

Statement of Work (SOW)

Version: 1.0

Date: 21 November 2025

1. Project Overview

ACME Manufacturing is rolling out Salesforce Sales Cloud and Service Cloud to replace fragmented CRM tools and spreadsheets.

The initial rollout will focus on the US sales and customer service teams (~150 users) with a roadmap for EMEA and APAC.

Primary goals:

- Provide a single source of truth for Accounts, Contacts, Opportunities and Cases.

- Standardize the lead-to-order and case-to-resolution processes.

- Improve visibility on pipeline, win/loss, and service SLA performance.

- Reduce manual activities around lead assignment and customer follow-ups.

2. Objectives

- Implement a scalable Salesforce Sales Cloud and Service Cloud solution aligned to ACME’s sales and service processes.

- Migrate high-value customer data from legacy CRM and spreadsheets.

- Integrate Salesforce with the ERP system for order and invoice visibility.

- Enable key reports and dashboards for Sales Leadership and Service Management.

- Train ACME admins and power users to support the platform post go-live.

3. In Scope

The following items are explicitly in scope for this engagement:

3.1 Salesforce Clouds & Features

- Sales Cloud (Leads, Accounts, Contacts, Opportunities, Activities).

- Service Cloud (Cases, Email-to-Case, basic knowledge).

- Basic Experience Cloud site for case submission (customers) – single brand.

3.2 Processes

- Lead capture from web forms and events.

- Lead qualification and assignment based on region and product line.

- Opportunity management from qualification to closure.

- Case management including triage, assignment, SLA tracking and resolution.

- Standard approvals for discounts on high-value deals.

3.3 Integrations

- One-way nightly batch integration from ERP to Salesforce for Orders and Invoices.

- One-way nightly batch integration from ERP for Product and Price Book updates.

3.4 Data Migration

- Migration of active Accounts and Contacts (last 3 years).

- Migration of open Opportunities and open Cases.

- Migration of core reference data (Products, Price Books, Regions).

3.5 Deliverables

- Configured Salesforce org (Sales & Service).

- Integration jobs and mappings.

- Data migration scripts and one test load + one final cutover load.

- Training sessions for admins and key users (remote).

- Solution overview and configuration workbook.

4. Out of Scope

The following are out of scope:

- CPQ implementation.

- Field Service implementation.

- Full multi-brand customer community.

- Custom mobile applications.

- Real-time bi-directional ERP integration.

5. Assumptions

- ACME will provide a single product owner empowered to take decisions.

- ACME will provide sample data and mapping rules in a timely manner.

- ACME will provide access to ERP environments and integration endpoints.

- ACME power users will participate in UAT and sign off within the agreed timelines.

6. Dependencies

- Availability of ACME SMEs from Sales, Service and IT.

- Timely provisioning of integration credentials (API keys / VPN / certificates).

- Approval of data migration mapping templates before test load.

7. Risks & Mitigations (High Level)

- Risk: Integration delays due to ERP API limitations.

Mitigation: Start integration analysis in Week 1; use stub services for early testing.

- Risk: Poor data quality delays cutover.

Mitigation: Run early profiling on sample data; agree cleansing rules by Week 2.

- Risk: Limited internal admin capacity.

Mitigation: Conduct hands-on enablement early; provide admin playbook.

8. Pricing

This engagement is based on a time-and-materials model with a capped effort.

Estimated effort:

- Engagement Director: 20 hours

- Project Manager: 120 hours

- Solution Architect: 160 hours

- Business Analyst: 200 hours

- Salesforce Developers: 400 hours

- QA Engineer: 160 hours

Blended rate assumption:

- Onshore rate: 180 USD/hour

- Offshore rate: 65 USD/hour

- Effective blended rate (approx): 95 USD/hour

Total estimated services fee:

- 1,060 hours x 95 USD/hour ≈ 100,700 USD

9. Payment Terms

- 30% on project start.

- 40% on completion of UAT.

- 30% on go-live.

10. Change Control

Any changes to scope, timeline, or assumptions will be managed through a formal Change Request (CR) process, including impact assessment on effort, cost and schedule.